Status Report

for:

Deutsche Telekom AG
Group Technology
- Ian Farrer -
Landgrabenweg 151
D-53227 Bonn

about:

OpenCPE
Development Service

by:

Travelping GmbH
Röntgenstraße 13
39108 Magdeburg

Contact:

Marion Krämer
Holger Winkelmann

Tel.:	+49 (391) 819099-232

Date: 28.03.2014

# Status Report OpenCPE
The following report will document the current status of development based on the deliverables time schedule and further conclusions made after workshops and conference calls.
## Time Schedule
The following section describes the delivery milestone that must be met by Travelping.
Meilenstein	Bereitstellung (BZA)
3.1 YANG Device Modeling	03.02.2014
3.2 Device Manager	31.03.2014
3.3 - removed by addendum -
3.4 OpenWRT Integration (formally Distribution)	30.04.2014
3.5 - removed by addendum -
3.6 OpenSource Activities	31.07.2014

# Reporting
The status of the individual deliverables are color coded.
Green: Status Ready
Orange: Status Ongoing
Red: Status Critical
Grey: Status neutral or descoped
Blue: Notes
# Deliverables
## YANG Modeling
Deliverables:
The Deliverable for the “Development of a Yang model” milestone is a YANG data model with the following characteristics:
- Base YANG models for a Terastream CPE, building the root element and container for the IETF YANG model drafts described above.
- CPE Use cases: The existing IETF data models will be extended as required for CPE specific functions necessary for implementing the use cases described in Section 4 of this document.
Travelping is encouraged to work with relevant 3rd parties who have specific expertise in the area of YANG model development as part of this work. DT can facilitate this discussion.
The YANK Models are developed, reviewed and accepted. The final models are published are published [1] and used as the working assumption for further development of the OpenCPE device management.
[1] OpenCPE YANG Models: https://github.com/opencpe/yang
After the implementation it is the intention to publish the YANG models as OpenSource and present the models to IETF for standardisation.
## NETCONF/YANG Device Management
Deliverables:
The deliverable of the “NETCONF/YANG Device Management” milestone is a OpenWRT based software, that can be installed on a supported Homegateway running OpenWRT from the current OpenWRT development trunk. The Software implements the following functionality:
An initial ‘Hello world’ connection between the NETCONF Server and the CPE to prove connectivity
The initial “Hello World” connection between the NETCONF protocol agent “freenetconfd” and the NCS Server is ready and presetend over IPv4 and Ipv6 connectivity. The initial capabilities are announced. The Authentication of the SSH connection between NCS and NETCONF agent is possible by user/password and NCS presented SSH Key.
Open Topics: The question of a global SSH Key used for deployment to the CPE is open. Currently we are using a user centric SSH Key on the NCS for the “admin” user.
Bootstrap the NETCONF agent using provided configuration
The NETCONF protocol agent has a local configuration for bootstrapping to accept the SSH Key of the NCS and configures the NCS Server.
Secure device identification (i.e. SSH key)
In our discussion we descoped this topic and allow all port knocking CPEs to connect for a NETCONF session. SSL DeviceCertificate and CPE based Keys was not a option.
All YANG models developed in 3.1 will be implemented in device manager
The YANG model are implemented in the device manager “mand”. To allow extendability, the device manager model will be generated directly from the YANG models. This way model changes can be generated and directly compiled for a CPE image. The device managed “mand” is published [1] as open source. The generator for the device manager models is provided [2] as plugin for the de facto standard YANG validator pyang [2] and part of the mand repository [3]. A example of the structures generated by the pyang plugin based on the OpenCPE model will be part of the repository [].
Its envisioned to publish the “mand” code open source as well as part of the OpenCPE or OpenWRT project.
[1] https://github.com/travelping/mand
[2] https://code.google.com/p/pyang/
[3] https://github.com/travelping/mand/tree/master/yang
[4] https://github.com/travelping/mand …. please add correct Link
All functions implemented in Device Manager will be integrated with the OpenWRT management framework if exposed by the UCI/ubus APIs. (see above)
Most of the functions available in UCI are implemented in a configuration agent “mand-cfgd” [1] which integrates OpenWRT based configs with the models in the device manager. The agent also acts as skeleton for further integration work for non UCI exposed values in OpenWRT. This work is ongoing as part of the OpenWRT integration work.
Parts of this functionality can be shown based on a command line tool provided with “mand” the change of the UCI values will be seen. However a full demo i.e. incl. The Interface stack is only possible on a finally integrated device i.e. EA4500.
As list off missing model nodes will provided based on the Excel Table [2]of the OpenCPE models.
[1] https://github.com/travelping/mand-cfgd
[2] <please add reference to list>
Identify any necessary functions not exposed by the UCI/ubus APIs and provide a specification for how these functions need to be implemented in UCI/ubus.
A Excel table has beed created and agreed to show the currently not UCI exposed configuration nodes of the OpenCPE model.
Device manager / OpenWRT management integration necessary to achieve the use cases described in section 4 of this document
The initial connection to the NCS has not been developed yet. A connection to the NCS can be established by running either a init and cron based netcat script. This would become part of the OpenWRT integration.
NETCONF protocol as device manager front end for CPE configuration.
The NETCONF protocol agent is able to make NETCONF over SSH connection coming from the NCS server. The Integration with with the device manager is working for the model nodes in the openCPE models. The integration of this two parts has faced some problems in the APIs between “mand” and “freenetconfd” which are being worked on.
The expected delivery date will be: __.04.2014
The descriped problems of the API faced further a problem with new additional RPC in YANG models which go behind the model access (i.e. firmware update RPC) This causes work on the extension of API which is currently ongoing.
The expected delivery date will be: __.04.2014
IPC and API integration point for communication between device manager, service manger and configuration agents.
The mand API has been provided [1] and a implementation of a library [2] exists as part of the “mand” project:
[1] http://travelping.github.io/mand/
 [2] https://github.com/travelping/mand/tree/master/libdmconfig

## BSP Integration and Development
Deliverables:
Section 3.3 “BSP Integration and Development” has no deliverable.
## OpenWRT Integration (formally Distribution)
Deliverables:
The deliverable of section 3.4 is an OpenWRT conforming package(s) that can be used to install the software developed as part of this contract in an OpenWRT environment.
While the delay of the freenetconfd – mand is happing on the API level work has been started to integrate the software components “freenetconfd”, “mand”, “mand-cfgd” and the pyang based model transformation with OpenWRT tool chain. The recipes for packaging have be written and compile for the given OpenWRT toolchain.
While discussing the integration startegy it was faced that part of the integration work will be device specific. (I,e, firmware update on EA4500). This device specific elements will be separated from the device management self but become part of the integration work.
For demonstration of the functionality the project decided to build the software for a Cisco EA4500 target. As mentioned some of the components are device specific. Further the Interface stack used in Terasteam will be modeled and configured with the OpenCPE YANG models. This integration work is ongoing but not seen on a critical path.
## OpenCPE Environment
Deliverables:
Section 3.5 “OpenCPE Environment” has no deliverable
## OpenSource Activities
Deliverables:
The deliverables of section 3.6 are:
- Formal contribution to the OpenWRT open source community of the deliverables of section 3.2. and 3.4.
- For up to 3 months after submission of the formal contribution, active participation in promoting the adoption of deliverables of section 3.2. and 3.4.
The activities to open source the YANG models and component has been started already while development. The current state of development is public and all development and integration is already based on the public repositories. To facilitate direct integration with OpenWRT discussions with OpenWRT community has been started. There are currently two options to drive the OpenWRT integration:
1. become part of the core of OpenWRT.
2. Provide recipes being part of OpenWRT but the components self are maintained and provided by OpenCPE.

# Use Case Description
The following section of the document describes the use cases that have been defined as relevant for the project during the meeting between Travelping and Deutsche Telekom on the 31st of July. The text for the descriptions is taken directly from the resulting agreements following this meeting.
Where relevant, the text in the main body of this document updates the Use Case descriptions given here.

Use Case 1: Bootstrapping, Registration of HG at the Network Configuration Server (NCS)

Discovery of NCS via DHCP (IP address or DNS FQDN or DNS SRV record).
- “Call home” of HG to NCS (establish SSH (?) connection, exchange Netconf “hello”) NCS requests HG ID
- HG replies and gets registered with NCS (Periodically refreshing the registration at the NCS)

Use Case 2: Request / Signaling of HG OS version to NCS Short description

- In context of registration or after registration
- NCS request Home Gateway to send result of “uname –a” output towards the NCS.
- HG replies and NCS stores “uname –a” information together with HG parameters in its DataBase.

Use Case 3: Firmware Upgrade via Netconf

- NCS sends HG a request to upgrade its firmware with a new one that can be found under a certain URI within the next x minutes.
- HG ACKs and triggers the firmware download randomly within this time interval.
- After successful firmware download and HG upgrade the HG reboots and runs again through the standard NCS register process.
- (If needed the HG may send an additional NETCONF “Notify” to the NCS in order to explicitly signal the successful upgrade.)